EMISSIONS INVENTORY DEVELOPMENT CONTRACT

JULY 2003

PURPOSE: The purposes of this contract are to assist in developing emission inventories by performing related work and to aid Mid-Atlantic-Northeast Visibility Union (MANE-VU) members in developing 2002 haze precursor emission inventories in a regionally consistent manner.  MANE-VU requires a consistent and comprehensive emissions inventory for the entire eastern United States.  The contractor will also coordinate similar work in other RPOs.

E.H. Pechan & Associates (Pechan) is the contractor for this project.  This contract allows for varied work assignments.  MARAMA will assign tasks in through work assignments negotiated with the contractor.  The contract will expire on August 15, 2003, but is renewable for up to three consecutive years.

WORK ASSIGNMENT 1: Under the first task of this contract, Pechan developed a work plan to prepare 2002 mobile and non-road emissions inventories for the MANE-VU states.  The results of this project are intended to be used in regional haze SIPs, with the possibility of being used in PM10, PM2.5 and 8-hour ozone SIPs.  Much of the data needed to estimate mobile source emissions to support regional haze programs are the same as those used to estimate mobile source emissions of ozone precursors, however regional haze requires inventories that cover the entire year and the entire region.  The work plan will be used to define needs for contractor assistance to augment state efforts.

The deliverable for this work assignment was a final work plan titled “Work Plan for Preparation of a 2002 Mobile Source Emissions Inventory for the Mid-Atlantic/Northeast Visibility Union (MANE-VU)” and Quality Assurance Project Plan (QAPP) for the development of a 2002 onroad and nonroad emission inventory for the MANE-VU States.  The work plan and QAPP were completed in January 2003 and are available on the MARAMA website.

WORK ASSIGNMENT 2:  Based on the work that Pechan did under the first work assignment under this project, MARAMA is drafting a work assignment for Pechan to undertake the tasks outlined in the Mobile Sources Work Plan.

The tasks under this work assignment are scheduled to begin in November 2003 by summarizing the default data used by EPA in the NEI.  In December 2003, the contractor will begin collecting, compiling and reviewing the data submitted by the states and tribes.  The bulk of the tasks under Work Assignment 2 will occur in Year 5.

TECHNICAL OVERSIGHT COMMITTEE: Ray Malenfant of Delaware, Kevin McGarry and Kevin Watz of New York, Dean Van Orden of Pennsylvania, Jeff Merrell of Vermont, and Annie Baumann and Susan Wierman of MARAMA

DELIVERABLES:  The work plan and QAPP were completed in January 2003, and are available on the MARAMA website.  Upcoming tasks, pending work assignment finalization, include; summarizing default mobile data in November 2003, and compiling state submitted mobile data in December 2003.

CONTACT INFORMATION:

Annie Baumann, MARAMA, abaumann@marama.org, 410-467-0170

Maureen Mullen, E.H. Pechan & Associates, mmullen@pechan.com, 703-813-6700